DECORA POWDER COATINGS

CoatPro ERP

3-Week Implementation & Go-Live Plan

Version 1.0  |  March 8, 2026

CONFIDENTIAL

For internal use only

# Executive Summary

This document outlines a 3-week plan to take the CoatPro ERP from development to full production use at Decora Powder Coatings. The plan covers team responsibilities, data collection requirements, workflow configuration, testing phases, and go-live procedures.

The goal is to have all core users entering real data by the end of Week 3, with ongoing feature improvements driven by actual usage patterns and feedback.

# Team Roles & Responsibilities

Every team member has a specific role in making the ERP operational. Here is what each person needs to do and when.

| Role | Person(s) | Week 1 Tasks | Week 2 Tasks | Week 3 Tasks |
| --- | --- | --- | --- | --- |
| Owner / Admin | Brock | Collect master data, configure users & roles, review all modules | Approve workflows, validate reports, train managers | Monitor adoption, gather feedback, prioritize fixes |
| Office Manager | TBD | Enter customer master data, set up payment terms & tax codes | Enter vendor data, configure invoice templates | Begin daily invoicing, AP/AR entry |
| Shop Floor Supervisor | TBD | Review job workflow stages, validate status pipeline | Test job creation & status transitions, train operators | Oversee daily job entry, report issues |
| Quality Manager | TBD | Review QC inspection forms, define compliance standards | Test QC workflow (inspect, pass/fail, NCR), enter equipment specs | Daily inspections in system, cure log entries |
| Operators (2–4) | TBD | Attend 30-min training session, practice receiving kiosk | Shadow-run: enter jobs alongside paper process | Full adoption: all job updates in ERP |
| Sales / CRM | TBD | Review CRM pipeline stages, import existing contacts | Enter active opportunities, test quote-to-job flow | Daily CRM activity logging, follow-up tracking |
| Accounting | TBD | Review chart of accounts mapping, QB tax codes | Test invoice export to QuickBooks, validate tax calcs | Begin using QB export for real invoices |
| Maintenance Tech | TBD | Review equipment records & work instructions | Test work order creation, PM schedule accuracy | Log all maintenance work orders in system |

# Week 1: Data Collection & Configuration (Mar 10–14)

Goal: Load all master data into the ERP so the system reflects reality. No one uses the ERP for daily work yet—this is setup week.

## Data Brock Needs to Collect

Bring this data back in any format—spreadsheet, photos of whiteboards, paper lists, or just typed notes. I will format and import it.

### 1. Customer Master List

| Field | Example | Required? |
| --- | --- | --- |
| Company name | ABC Fabrication Inc. | Yes |
| Primary contact name | John Smith | Yes |
| Contact email | john@abcfab.com | Yes |
| Contact phone | 555-0101 | Yes |
| Billing address | 123 Industrial Blvd, Detroit MI 48201 | Yes |
| Shipping address (if different) | 456 Warehouse Dr | If different |
| Payment terms | Net 30 | Yes |
| Tax exempt? If yes, cert # | No / Cert #12345 | Yes |
| Credit limit | $10,000 | Optional |
| Notes / special instructions | Requires CoC on every order | Optional |

### 2. Vendor / Supplier List

| Field | Example | Required? |
| --- | --- | --- |
| Company name | Tiger Drylac Canada | Yes |
| Contact name & email | Jane Doe, jane@tiger.com | Yes |
| Phone | 555-0202 | Yes |
| What they supply | Powder coatings, primers | Yes |
| Payment terms | Net 45 | Yes |
| GST/HST number | 123456789RT0001 | If applicable |
| Currency | CAD / USD | Yes |

### 3. Inventory / Powder Stock

| Field | Example | Required? |
| --- | --- | --- |
| Product name / color | Tiger 049/70049 Gloss Black | Yes |
| SKU or internal code | BLK-GLOSS-001 | Yes |
| Category | Powder / Chemical / Consumable | Yes |
| Current quantity on hand (kg or units) | 45 kg | Yes |
| Unit cost | $12.50/kg | Yes |
| Reorder point (when to buy more) | 10 kg | Yes |
| Reorder quantity | 50 kg | Optional |
| Lot number (if tracking) | LOT-2026-0301 | Optional |
| Storage location | Rack A, Shelf 3 | Optional |
| Supplier name | Tiger Drylac | Yes |

### 4. Employee / User List

| Field | Example | Required? |
| --- | --- | --- |
| Full name | Sam Chen | Yes |
| Email (@decorapowdercoatings.com) | sam@decorapowdercoatings.com | Yes |
| Role | operator / manager / admin / sales / viewer | Yes |
| Department | Production / Quality / Sales / Admin | Yes |
| Phone (optional) | 555-0303 | Optional |
| Hourly rate (for job costing) | $28/hr | For operators |

### 5. Service Pricing

Powder coating rates: per sq ft, per part, per rack, or per job—however you price today

Sublimation rates: per sq ft or per piece

Add-on charges: blasting, masking, rush surcharge, re-coating, special packaging

Minimum order / setup fee: if applicable

### 6. Active Jobs (Current Work in Progress)

A snapshot of all jobs currently on the floor or awaiting shipment. For each:

Customer name and PO number

Part description and quantity

Powder color / spec

Current stage (blasting, coating, curing, QC, shipping)

Due date

Sale price (if known)

### 7. Equipment Details (Nice to Have)

We already have GEMA equipment records loaded. For any other equipment:

Name, model, serial number

Location on the floor

Last maintenance date

Any known maintenance schedules

## Week 1 Configuration Tasks (Brock + Claude)

Import customer master data into ERP

Import vendor/supplier data

Import inventory with current stock levels

Create user accounts with correct roles (RBAC)

Configure pricing rules and tax jurisdictions

Set up custom dropdowns (finish types, materials, etc.)

Verify QuickBooks chart of accounts mapping

Load active WIP jobs into the system

Test login from multiple devices via coatpro.app

## Management Demo (End of Week 1)

Target: Friday, March 14 — 30-minute walkthrough with management team

Dashboard: Live KPIs with real customer and job data

Job lifecycle: Create a job, move through stages, complete it

Invoicing: Generate invoice, show QB export

Maintenance: Show work orders, PM schedule, equipment health

Export: Download jobs/invoices to CSV from any table

Access: Everyone logs in from their own device via coatpro.app

# Week 2: Parallel Run & Training (Mar 17–21)

Goal: Run the ERP alongside existing paper/spreadsheet process. Staff enter data in both systems. Identify gaps and fix them in real time.

## Training Schedule

| Day | Session | Audience | Duration | Topics |
| --- | --- | --- | --- | --- |
| Monday | Admin Training | Brock + Office Mgr | 1 hour | User management, backups, settings, QB export |
| Monday | Shop Floor Intro | All operators | 30 min | Login, receiving kiosk, job status updates |
| Tuesday | Quality Training | QC Manager | 45 min | Inspections, NCR workflow, cure logs, certificates |
| Tuesday | CRM Training | Sales team | 30 min | Pipeline, activities, quotes, follow-ups |
| Wednesday | Maint. Training | Maint. tech | 30 min | Work orders, PM schedule, parts tracking |
| Wednesday | Accounting Training | Office Mgr | 30 min | Invoicing, payments, QB CSV export |
| Thu–Fri | Supervised Production | All staff | All day | Real data entry with Brock available for questions |

## Parallel Run Rules

Every job that arrives gets entered in the ERP AND the existing paper/spreadsheet process

At end of each day, compare: does the ERP match reality? Flag any discrepancies

Brock collects a feedback list from each user (what was confusing, what was missing, what broke)

Claude fixes reported issues same-day or next morning

No data is deleted during parallel run — everything is preserved for validation

## Feature Completion During Week 2

While users are testing, we continue building features in the background:

Labor time tracking on jobs: Operators log hours per job directly in the ERP

Configurable dashboard: Each user picks which KPI cards matter to them

Excel export: All major tables export to .xlsx (not just CSV)

Bug fixes: Anything found during parallel run gets fixed immediately

# Week 3: Go-Live & Full Adoption (Mar 24–28)

Goal: Stop the paper process. The ERP is the single source of truth. All data entry happens in CoatPro.

## Go-Live Checklist

| # | Item | Owner | Status |
| --- | --- | --- | --- |
| 1 | All customers imported and verified | Office Mgr | ☐ |
| 2 | All vendors imported | Office Mgr | ☐ |
| 3 | Inventory counts verified (physical count vs ERP) | Shop Supervisor | ☐ |
| 4 | All user accounts active with correct roles | Brock | ☐ |
| 5 | Automated backups running every 6 hours | Brock | ☐ |
| 6 | Cloudflare tunnel auto-starts on ROG boot | Brock | ☐ |
| 7 | Sleep mode disabled on ROG PC | Brock | ☐ |
| 8 | QB export tested with real invoice | Accounting | ☐ |
| 9 | All staff can log in from their devices | All | ☐ |
| 10 | Emergency recovery playbook printed and posted | Brock | ☐ |
| 11 | Paper forms officially retired | Brock | ☐ |
| 12 | Week 2 feedback items all resolved or documented | Brock + Claude | ☐ |

## Daily Workflow After Go-Live

### Morning (Start of Shift)

Supervisor checks Dashboard: overdue jobs, rush orders, low stock alerts

Receiving operator logs incoming shipments via Receiving Kiosk

Admin reviews Pending Job Queue, confirms jobs to release to production

Operators check their assigned jobs on Production Board

### During Production

Operators update job status as parts move through stages (blast → coat → cure → QC)

QC Manager enters inspection results; passes or creates NCR for failures

Maintenance tech logs any unplanned work orders

Sales enters CRM activities (calls, emails, follow-ups)

### End of Day

Office Manager creates invoices for completed jobs

Supervisor reviews daily throughput on Dashboard

Accounting exports invoices to QuickBooks (weekly or as needed)

Brock reviews audit log for any issues

### Weekly

Management reviews Reports tab: revenue trend, margins, AR aging

Quality Manager reviews PM compliance and equipment health

Brock and Claude review user feedback, plan next feature sprint

# Data Migration Strategy

Data migration happens in stages to minimize risk. We never bulk-import without verification.

| Data Set | Source | Import Method | Verification | Week |
| --- | --- | --- | --- | --- |
| Customers | Spreadsheet or QB export | CSV import via Admin Console | Spot-check 10 records, verify contacts | 1 |
| Vendors | Spreadsheet or QB export | CSV import via Admin Console | Verify payment terms, tax numbers | 1 |
| Inventory | Physical count + spreadsheet | Manual entry or CSV import | Physical count matches ERP within 5% | 1 |
| Users | Employee list | Manual entry in Admin Console | Each person logs in successfully | 1 |
| Active jobs (WIP) | Whiteboard / spreadsheet | Manual entry in Jobs module | Supervisor confirms all active jobs present | 1 |
| Historical invoices | QuickBooks | QB CSV import (optional) | Spot-check totals match QB | 2 |
| Equipment / PM data | Already loaded (GEMA) | Verify accuracy | Maintenance tech confirms schedules | 2 |
| CRM contacts & history | Sales spreadsheet / email | Manual entry in CRM | Sales confirms key accounts present | 2 |

## Data Quality Rules

No duplicate customers: Check by name before importing. The system prevents duplicate emails.

Currency consistency: All prices in CAD unless customer is explicitly USD.

Date format: YYYY-MM-DD (ISO 8601) for all dates.

Required fields: Customer name + contact email are mandatory. Jobs need customer + due date + service type.

Inventory accuracy: Do a physical count before import. The ERP is only as good as its data.

# Testing Plan

## Week 1 Testing (Admin / Config Testing)

| Test | Steps | Expected Result | Tester |
| --- | --- | --- | --- |
| Login from mobile | Open coatpro.app on phone, enter email, get OTP | ERP loads, dashboard visible | Brock |
| Create customer | Customers → New → Fill form → Save | Customer appears in list, persists after refresh | Office Mgr |
| Create job | Jobs → New Job → Select customer, fill details | Job appears with correct status | Brock |
| Export to CSV | Jobs table → Click Export | CSV downloads with correct data | Brock |
| Create invoice | Invoicing → New → Select completed job | Invoice with correct totals and tax | Office Mgr |
| QB export | Invoicing → Export to QuickBooks | CSV file imports cleanly into QBO | Accounting |
| Backup/restore | Admin Console → Backups → Download | JSON backup downloads, can be restored | Brock |
| Role permissions | Log in as operator, try to access Admin Console | Access denied for admin-only features | Brock |

## Week 2 Testing (Workflow Testing)

| Test | Steps | Expected Result | Tester |
| --- | --- | --- | --- |
| Full job lifecycle | Receive → Prep → Blast → Coat → Cure → QC → Ship → Complete | Job progresses through all stages | Supervisor |
| QC pass/fail | Quality → Inspect job → Fail → NCR → Rework | NCR created, rework tracked | QC Mgr |
| Inventory adjustment | Receive powder → Use on job → Check stock | Stock decreases correctly | Operator |
| Maintenance WO | Create WO → Add labor → Add parts → Complete | Parts deducted, cost calculated | Maint. Tech |
| CRM follow-up | Log call → Schedule follow-up → Check Today tab | Follow-up appears on due date | Sales |
| Multi-device sync | Update job on tablet, check on desktop | Change visible within 5 seconds | Brock |
| Stress test | 3 users entering data simultaneously | No data loss or conflicts | All |

# Ongoing Improvement Process (Week 4+)

After go-live, the system improves continuously based on real usage data.

## Feedback Collection

Weekly feedback form: Simple 3-question form (What worked? What didn’t? What’s missing?) shared with all users every Friday

Issue tracker: Brock maintains a prioritized list of bugs and feature requests

Usage analytics: Track which modules get used, which get ignored — optimize accordingly

## Feature Roadmap (Post Go-Live)

| Priority | Feature | Timeline | Impact |
| --- | --- | --- | --- |
| High | ADP payroll integration (employee sync) | Month 2 | Eliminates double-entry for HR |
| High | QuickBooks OAuth (live sync, not CSV) | Month 2 | Real-time AR/AP in QB |
| High | PDF invoice & quote generation | Month 2 | Professional customer-facing docs |
| Medium | Barcode scanning at receiving | Month 2–3 | Faster receiving, fewer errors |
| Medium | Customer portal (read-only job status) | Month 3 | Customers self-serve status checks |
| Medium | Low-stock auto-alerts (email/SMS) | Month 3 | Never run out of powder |
| Lower | Mobile operator app | Month 4+ | Optimized touch UI for shop floor |
| Lower | SAT MySQL integration | Month 4+ | Sync with existing coating line software |
| Lower | Advanced forecasting | Month 6+ | ML-based demand prediction |

## Automation Opportunities (Driven by Data Trends)

As users enter data, patterns emerge that we can automate:

Auto-reorder: When powder stock hits reorder point, auto-generate a PO draft for the preferred vendor

Auto-schedule maintenance: When equipment runtime hits threshold, auto-create a work order

Invoice reminders: Auto-flag overdue invoices and prompt the office manager

Job costing alerts: When actual labor exceeds estimate by >20%, alert the supervisor

CRM follow-up reminders: Auto-prompt sales when a quoted opportunity has had no activity for 7 days

Production bottleneck detection: Flag when jobs pile up at a specific stage (e.g., QC) consistently

# Risk Mitigation

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| ROG PC goes offline (power, sleep, crash) | Medium | High | Startup script auto-launches services; sleep disabled; UPS recommended |
| User enters wrong data | High | Medium | All changes logged in audit trail; admin can edit/revert; training covers common mistakes |
| Internet outage (Cloudflare tunnel down) | Low | High | ERP falls back to localStorage; data syncs when connection returns; local network access still works |
| Supabase free tier limits exceeded | Low | Medium | Monitor usage; upgrade to Pro ($25/mo) if needed; server backups independent of Supabase |
| Staff resistance to new system | Medium | High | Parallel run reduces pressure; training is hands-on; feedback is acted on quickly; champion users help others |
| Data loss during migration | Low | Critical | Full backup before any import; never delete source data; checksum verification on all backups |

# Support & Contacts

| Resource | Details |
| --- | --- |
| ERP URL | https://coatpro.app |
| API URL | https://api.coatpro.app |
| Supabase Dashboard | https://supabase.com/dashboard |
| Cloudflare Dashboard | https://dash.cloudflare.com |
| GitHub Repository | https://github.com/brock-prog/erp (private) |
| Server Ops Guide | docs/plans/2026-03-08-server-ops-guide.md |
| Emergency Recovery | See Section 6 of Server Ops Guide |

This document is a living plan. It will be updated as we progress through each week. Next review: end of Week 1 (March 14, 2026).